## Sheet1
Question | Your Response
Planning:
How do you track outage preparation? | We have site milestones which include some RP actions and also have an RP procedure of actions and due dates to drive readiness
How are RP actions tracked and assigned? (e.g. corrective action program, procedure, excel spreadsheet, meeting minutes, etc.) | We have our outage readiness action in excel spreadsheet
What does your ramp-up for RP outage preparations look like? | Weekly dept meetings start approx 4mths prior to outage. Actions due prior are tracked/discussed in one off dept meetings
At what frequency do you conduct RP outage readiness meetings? | Weekly starting about 4 mths prior
What type of benchmarking is performed to prepare for outages? | Fleet lessons learned are shared and reviewed
What are their milestones for ALARA plans being prepared by? | All WO's assigned 14 weeks prior. Alara plans thru SAC 1mth prior
What does your outage org chart look like - meaning, How are your outage supervisors assigned, do you have a superintendent on each shift over the supervisors? | RP Ops Mgr is usually RPM on nites. Have 4 Supvs per shift normally; duty desk/Aux Bldg, Loer Cnmt, Upper Cnmt, Contamination Controls
Do you put out an ‘Outage Book’ to the site? Or RP? Or both | A RP outage book for RP
Do you do any JITT for contractors to familiarize them with your site procedures, expectations, instruments, and processes (like VSDS, HIS-20/Sentinel, etc.) | Alpha, airsampling, electron capture usually
When are ALARA Plans required to be completed? | Ones going to SAC 1 mth prior to outage. Others about then but some get final approvals a week out based on manning and available resources
When are RWPs required to be completed? | Same as alara plans
How do you handle mass RWP Briefings? | Ususally those briefs are done along with IPAs or HLAs
RWP Briefing frequency? | Shiftly. We do approve some tasks weekly depending on task and radiolodical risk and changing conditions
Is RWP Briefing frequency different than outage? | Online all shiftly
Do you allow any RWP self-briefing? | Yes for Aux designated seld brief areas
How are your outage RWP’s structured? What is your site rollout plan for outage RWP’s look like? | RWPs by dept and by overall tasks. Each RWP may have multiple tasks within to allow for difference in settings and controls
How long in advance do they transition techs to control points? | Techs usually start 6-12s two weeks prior
Personnel:
What does your ramp up and ramp down curve look like for staffing? | Week prior usually get 8SR and 6JR techs. Then the rest the Thur before the outage. Alara and Supv staff few 2 weeks out and rest one week prior
Do you use contractors as RP supervisors or ALARA specialists used during your outages? | Yes, most of them retired Constellation employees
How do your utilities shared resources support your plant’s outage organization? | We target getting 24 RPTs from midwest sites and not always the case but on average 4 mgmt staff (RPS/alara)
What position within the RP organization staffs your Outage Control Center? | Varies - RP Programs Mgr, retired Constellation mgmt individuals
Implementation:
How are fatigue rules managed during outage? | We keep 3 ERO RPTs on days and nites and they rotate days off as covered workers. Everyone else working 7x12.5
How many control points do you operate? | 4 - upper cnmt, lower cnmt, Aux Bldg, and cnmt access facility
Are the control point coordinators house or contract personnel? | Both
Do you have dedicated techs for certain groups? For instance, OPS, carpenters, insulators, valve maintenance, etc. | Carps
How are RMS/ technology needs for the outages deployed and maintained throughout the outage? | We have a RMT program owner on days. Bring IIS and another Constellation traveler in for a few day to help deploy