## ONS
Question | Your Response
Planning:
How do you track outage preparation? | With months of meetings, pre-meeting meetings, and meetings after the meetings. ALARA Planners (2 of us) attend HIT teams for ISI, SG, Alloy 600, MRP-227, weekly Outage Review Board, T-6, T-3, T-1 Fleet Reviews. Luckily Teams allows you to join 1 on your phone and another on your laptop so we don't neglect our Online planning duties.
How are RP actions tracked and assigned? (e.g. corrective action program, procedure, excel spreadsheet, meeting minutes, etc.) | Action Items are assigned in NTM's in Nuclear Asset Suite, and recently Fleet developed something called Scheduling, Planning, and Cost Estimation (SPaCE). Now we document all actions twice.
What does your ramp-up for RP outage preparations look like? | We have 1 job coverage RP tech assigned to outage planning for the RP group (supplies, Decon, coverage plans).
At what frequency do you conduct RP outage readiness meetings? | Usually one a couple of weeks before the outage.
What type of benchmarking is performed to prepare for outages? | Very little. With 3 units there isn't much space between outages. Specific questions usually addressed on Global Bounce.
What are their milestones for ALARA plans being prepared by? | T-30 days
What does your outage org chart look like - meaning, How are your outage supervisors assigned, do you have a superintendent on each shift over the supervisors? | 1 Supt per shift, 3 supv per shift for Rx, Aux, and TB (due to legacy issues we post the outage turbine area as RCA/CA). Supvs are house techs, shared resources, or returnee contractor.
Do you put out an ‘Outage Book’ to the site? Or RP? Or both | There is a very extensive onboarding briefing given to all incoming RPs. Every outage we prepare a printed set of flush scripts.
Do you do any JITT for contractors to familiarize them with your site procedures, expectations, instruments, and processes (like VSDS, HIS-20/Sentinel, etc.) | JITT for glove bag/prep bag for fitters & RPs based on observed misuse here and the event at CGS.
When are ALARA Plans required to be completed? | Prior to job start
When are RWPs required to be completed? | T-1
How do you handle mass RWP Briefings? | Special large projects like Alloy 600 or MSRP Insp - RP briefs in crew area. All others come to briefing windows for various areas.
RWP Briefing frequency? | Shiftly unless conditions or scope changes occur.
Is RWP Briefing frequency different than outage? | No
Do you allow any RWP self-briefing? | Only on non-outage units. Outage unit self brief RWP set to inactive due to OE.
How are your outage RWP’s structured? What is your site rollout plan for outage RWP’s look like? | U1 1000 series, U2 2000 series, U3 3000 series. Separate RWPs for Rx and Aux, and one RWP to cover all of TB.
How long in advance do they transition techs to control points? | On outage day one. The night of shutdown everybody goes in Rx for initial survey. We follow other plants in the schedule, so our techs are usually still showing up the first week or 10 days of our outage.
Personnel:
What does your ramp up and ramp down curve look like for staffing?
Do you use contractors as RP supervisors or ALARA specialists used during your outages? | Yes
How do your utilities shared resources support your plant’s outage organization? | RP Techs, Lead Techs, and Remote Mon Techs.
What position within the RP organization staffs your Outage Control Center? | RP Staff Scientists
Implementation:
How are fatigue rules managed during outage? | Only applies to Shift (Tech Spec) RP techs. Everybody else takes a day off when they need one.
How many control points do you operate? | 3 - see #9
Are the control point coordinators house or contract personnel? | Yes
Do you have dedicated techs for certain groups? For instance, OPS, carpenters, insulators, valve maintenance, etc. | Scaffolds, SG, Alloy 600
How are RMS/ technology needs for the outages deployed and maintained throughout the outage? | 2 techs spend the first couple of days installing cameras and GEDDS detectors, then move to remote job coverage. No dedicated support during outage.