## Sheet #1
Question | Response: Braidwood | Response: Brunswick | Response: Harris | Response: Millstone | Response: Oconee | Column1 | Column2 | Column3
Planning:
How do you track outage preparation? | We have site milestones which include some RP actions and also have an RP procedure of actions and due dates to drive readiness | We use an excel spreadsheet. We have monthly meetings and then go to weekly meetings closer to the outage, usually about 2 - 3 months out. Utilize RP Outage Readiness Procedure | We use a fleet outage readiness procedure that I attached | We have an outage readiness checklist that we review weekly | With months of meetings, pre-meeting meetings, and meetings after the meetings. ALARA Planners (2 of us) attend HIT teams for ISI, SG, Alloy 600, MRP-227, weekly Outage Review Board, T-6, T-3, T-1 Fleet Reviews. Luckily Teams allows you to join 1 on your phone and another on your laptop so we don't neglect our Online planning duties.
How are RP actions tracked and assigned? (e.g. corrective action program, procedure, excel spreadsheet, meeting minutes, etc.) | We have our outage readiness action in excel spreadsheet | We use an outage readiness NTM in our CAP program to assign actions so we can track closure. NTM's have a route list. The individua(s) on route list, review documentation for accuracy and are the only persons that can approve closure. | Checklists in fleet procedure | Excel | Action Items are assigned in NTM's in Nuclear Asset Suite, and recently Fleet developed something called Scheduling, Planning, and Cost Estimation (SPaCE). Now we document all actions twice.
What does your ramp-up for RP outage preparations look like? | Weekly dept meetings start approx. 4mths prior to outage. Actions due prior are tracked/discussed in one off dept meetings | For outage preparations we use our normal compliment of RP personnel. We bring a few contractors in to help with scaffold builds & shielding, 5-6 weeks early and another 3-5 to support additional outage ramp up activities. Everyone else comes in the week the outage starts. We in- process on site. | We start about 6 months before an outage -- single unit site | Not fantastic. We have very limited resources, so prepping and staging is difficult. | We have 1 job coverage RP tech assigned to outage planning for the RP group (supplies, Decon, coverage plans).
At what frequency do you conduct RP outage readiness meetings? | Weekly starting about 4 mths prior | We do monthly 9 months out, twice a month approx. 5-6 months out, wkly 2-4 months prior to the outage based on the amount of actions we have coming due on the excel checklist. | At 6 months out, every 2 weeks. At 3 months out, weekly. | Weekly | Usually one a couple of weeks before the outage.
What type of benchmarking is performed to prepare for outages? | Fleet lessons learned are shared and reviewed | We benchmark activities that are infrequently performed and also look at the ALARA BWR owners group conference to look at new innovation to help improve. We review industry EO and make changes to our plans based on industry gaps. | Just fleet comparisons -- fleet outage management also performs a formal readiness assessment 3 months before outage | Nada | Very little. With 3 units there isn't much space between outages. Specific questions usually addressed on Global Bounce.
What are their milestones for ALARA plans being prepared by? | All WO's assigned 14 weeks prior. Alara plans thru SAC 1mth prior | BNP has a Fleet Outage Work Management Procedure that drives milestones. RP has a Fleet Outage Readiness Procedure that drives actions to closure | See checklist -- our milestones are synched with formal outage management milestones | We roll over our RWPs and ALARA Plans about 4 months in advance. Our dose is approved one month in advance. Then within two weeks of that we have a SAC to approve our ALARA Plans | T-30 days
What does your outage org chart look like - meaning, How are your outage supervisors assigned, do you have a superintendent on each shift over the supervisors? | RP Ops Mgr. is usually RPM on nights. Have 4 Supvs per shift normally; duty desk/Aux Bldg., Lower Ctmt, Upper Ctmt, Contamination Controls | We only have one superintendent. The shifts are ran by the supervisors. We have a BOP Supervisor, Reactor building Supervisor to include Torus Refuel Floor Supervisor, Drywell Supervisor and a Turbine Supervisor. We have had where we had an outside supervisor and one in the building when we run short. | 1 RPM per shift, 2 - 3 supervisors per shift (2 from fleet) | It's all over place. It depends on if we get other fleet support. 2 FLS each shift. Cal lab Supv and one of the FLS typically does OCC. ALARA Supv typically covers ALARA and unit. Both Supts act as observers... | 1 Supt per shift, 3 supv per shift for Rx, Aux, and TB (due to legacy issues we post the outage turbine area as RCA/CA). Supvs are house techs, shared resources, or returnee contractor.
Do you put out an ‘Outage Book’ to the site? Or RP? Or both | A RP outage book for RP | No we have a radworker handbook we have used in the past. We use ALARA plans and brief everyone coming in on the plans they are supporting. | We have a RadWorker tri-fold and RP is built into overall outage readiness briefing for departments (mainly safety topics) | Nope, OCC does. We do create a valve, snubber and weld book for the site | There is a very extensive onboarding briefing given to all incoming RPs. Every outage we prepare a printed set of flush scripts.
Do you do any JITT for contractors to familiarize them with your site procedures, expectations, instruments, and processes (like VSDS, HIS-20/Sentinel, etc.) | Alpha, air sampling, electron capture usually | We used to do this but it was eliminated, The NISP procedures are what we use. We do an initial discussion of OE and lessons learned when we can with our contract technicians. The RP Fleet Procedure has action to identify JITT needs. Activities such as Torus Diving, Radiography, etc. | No, nothing formal, just control point orientation by lead techs | Would be nice | JITT for glove bag/prep bag for fitters & RPs based on observed misuse here and the event at CGS.
When are ALARA Plans required to be completed? | Ones going to SAC 1 mth prior to outage. Others about then but some get final approvals a week out based on manning and available resources | Per procedure @ T-1. One month prior to outage start | see checklist | No specific due date, but at least two weeks in advance | Prior to job start
When are RWPs required to be completed? | Same as alara plans | (Per procedure) Pre-outage T-3/ Outage T-1 | see checklist | Same as above | T-1
How do you handle mass RWP Briefings? | Usually those briefs are done along with IPAs or HLAs | (Example) CRD push/pull & Cavity Decon briefings held 1-2 days prior to schedule start. This allows group to split shifts. Updated brief before jump. Refuel Fl personnel get a brief each time a crew changes out. They have 4 crews that stagger shifts. Others (1-10 persons) get required briefings in designated checkpoints. Reactor Bldg., DW, Refuel Fl have their own designated conference rms. TB currently in TB breezeway but looking to get designated conference area | We do some pre-outage, otherwise we have several dedicated briefing rooms | We do not - specifically only for refueling. Other than that we do it on a job to job basis | Special large projects like Alloy 600 or MSRP Insp - RP briefs in crew area. All others come to briefing windows for various areas.
RWP Briefing frequency? | Shiftly. We do approve some tasks weekly depending on task and radiological risk and changing conditions | Outside of Self Briefs: All personnel do a drive by for entries into RCA, All HRA/ LHRA get documented briefs each entry | Daily, but procedure includes a provision in which a supervisor can extend duration based on risk (low risk, just once per outage and a refresher when check-in with control point) | As required | Shiftly unless conditions or scope changes occur.
Is RWP Briefing frequency different than outage? | Online all shiftly | no | No | No, we brief for everything. The higher risk or IPTEs, we do a deeper dive, but we do it for outage and online. | No
Do you allow any RWP self-briefing? | Yes for Aux designated self brief areas | Yes we have the self brief RWP and routine RWPs are the responsibility of the Radworker to read and sign on. RP does not brief all RWP's. | Yes | Only for NRC and security | Only on non-outage units. Outage unit self brief RWP set to inactive due to OE.
How are your outage RWP’s structured? What is your site rollout plan for outage RWP’s look like? | RWPs by dept and by overall tasks. Each RWP may have multiple tasks within to allow for difference in settings and controls | We use same RWP #'s for respective units (unit 1 start with 1000 & unit 2, with 2000 series) | Same as on-line -- RWPs assigned to Wos | Each work group and specific jobs have RWPs - printed at RP brief area and on website | U1 1000 series, U2 2000 series, U3 3000 series. Separate RWPs for Rx and Aux, and one RWP to cover all of TB.
How long in advance do they transition techs to control points? | Techs usually start 6-12s two weeks prior | We start setting up the week before, techs are preparing there areas all year but start their control point the week of the outage as we get personnel. We go on a supershift 2 weeks prior to the outage. Meaning house personnel are on a modified shift coverage schedule on days and nights to be ready for the outage. | 2 weeks before outage | 2 weeks | On outage day one. The night of shutdown everybody goes in Rx for initial survey. We follow other plants in the schedule, so our techs are usually still showing up the first week or 10 days of our outage.
Personnel:
What does your ramp up and ramp down curve look like for staffing? | Week prior usually get 8SR and 6JR techs. Then the rest the Thur before the outage. Alara and Supv staff few 2 weeks out and rest one week prior | For outage preparations we use our normal compliment of RP personnel. We bring a few contractors in to help with scaffold builds & shielding, 5-6 weeks early and another 3-5 to support additional outage ramp up activities. Everyone else comes in the week the outage starts. We in- process on site. | Lately due to significant contractor shortages and fleet outage overlaps, we no longer have traditional ramp ups and downs | We bring in about 20% two weeks before. 20% one week before. And 60% the first week of the outage. We let about 20% go one week before the outage ends and then the rest the week that it ends. We typically will keep one or two techs afterwards.
Do you use contractors as RP supervisors or ALARA specialists used during your outages? | Yes, most of them retired Constellation employees | We use in house supervisors, shared resource supervisors and for ALARA we bring in contract ALARA support | ALARA yes, supervisors no (unless I know them well like a Duke retired supervisor) | We have used one Health Physicist as a Supervisor (didn't go well), but typically no. No contractors and my ALARA folks have no desire to be Supervisors. | Yes
How do your utilities shared resources support your plant’s outage organization? | We target getting 24 RPTs from midwest sites and not always the case but on average 4 mgmt. staff (RPS/alara) | We bring supervisors and technicians. | Yes, many | Because of the differences between regulated and non, it is a challenge. Currently, VCS supports us for one of outages. Usually 2-4 techs and 1-2 Supervisors. We are currently working with the VA plants to share resources. Our last U3 outage we received support from them. | RP Techs, Lead Techs, and Remote Mon Techs.
What position within the RP organization staffs your Outage Control Center? | Varies - RP Programs Mgr., retired Constellation mgmt. individuals | This is staffed by specialists, superintendents and chemistry staff | Staff RP and Chem scientists | Varies, but typically a Supervisor. At times, the Superintendent. | RP Staff Scientists
Implementation:
How are fatigue rules managed during outage? | We keep 3 ERO RPTs on days and nights and they rotate days off as covered workers. Everyone else working 7x12.5 | We have a crew that remans covered to support the outage and we uncover the others until we roll back to the on line rules then we cover everyone again. | All staff remains covered, we do 4 and 1 schedules for staff, 6 and 1 for contractors |  | Only applies to Shift (Tech Spec) RP techs. Everybody else takes a day off when they need one.
How many control points do you operate? | 4 - upper cnmt, lower cnmt, Aux Bldg., and cnmt access facility | Refuel, BOP building/ Outside BOP, Shipping, Drywell, Turbine, RB | 3 (4 if S/G work) | Two technically | 3 - see #9
Are the control point coordinators house or contract personnel? | Both | In house technicians to include shared resource techs as leads at some control points | House | House | Yes
Do you have dedicated techs for certain groups? For instance, OPS, carpenters, insulators, valve maintenance, etc. | Carps | We have a dedicated FIN tech. We do not have separate technician for the work groups, work is covered by the control points. | No, just refuelers | We try. | Scaffolds, SG, Alloy 600
How are RMS/ technology needs for the outages deployed and maintained throughout the outage? | We have a RMT program owner on days. Bring IIS and another Constellation traveler in for a few day to help deploy | Our instrument group which consist of 2 people maintain during the outage. We ask for a shared resource RMS tech to support 2 weeks prior to the outage and the initial weekend. | 1 techs per shift maintains equipment running (1 from fleet), we bring in several fleet technology RPs the week before an outage for setup & testing | We bring in a vendor (V3i) to assist us with setting up and maintaining CMS and comms. We have two techs that work the cameras and comms and two techs that assist with set up. | 2 techs spend the first couple of days installing cameras and GEDDS detectors, then move to remote job coverage. No dedicated support during outage.

## Sheet #2
Question | Response - BFN | Response - Ginna | Response - Salem | Response - Harris | Response - Wolf Creek | Column1 | Column2 | Column3
Planning:
How do you track outage preparation? | We follow the t-month process outlined in NPG-SPP-05.2.3 | Per a Procedure RP-AA-4002 RP Outage Preparation Readiness Checklist | It depends on which preparation. For specific jobs there are typically HIT teams (things like SGs and RVI work) which will have action item lists. For basic recurring outage work it is the normal work week/cap process. | See attached checklist | Milestones tracked by outage management.
How are RP actions tracked and assigned? (e.g. corrective action program, procedure, excel spreadsheet, meeting minutes, etc.) | CAP Program | Per the above Procedure | See above for some information. Lessons learned have an order in our CAP process following each outage. Some may be tracked on action item lists from various HIT teams. Some may be in recurring PM work orders. | Our ALARA techs work with supervisors to assign staff to applicable sections | CR's. Excel spread sheets
What does your ramp-up for RP outage preparations look like? | RCI-46 Radiation Protection Department Outage Preparation. |  | We offer some OT in the month leading up to the outage based on other work groups needing support or significant preps, other stuff we try to handle during the work day between other work. Our technicians split shifts the week before the outage so we have dedicated prep for that week as well | Typically we start getting pre-outage tasks assigned to maintenance/operations about a month or two before the outage and may require an extra 1-2 technicians in the main office | Bring in a few contract staff. (Dosimety, Alara)
At what frequency do you conduct RP outage readiness meetings? | Monthly starting at T-6. Weekly at T-2. | At least monthly | we don’t really have specific RP readiness meetings, we participate in the overall station meetings and HIT teams as required. | About 6 months out, meetings will be ~1/month. The frequency progressively increases up to 1/week before the outage. | frequency increases as outage gets closer. Monthly
What type of benchmarking is performed to prepare for outages? |  | Global PWR, email to other sites, phone calls | Benchmarking is performed as required, it usually will come from lessons learned from the prior outage or from suggestions from road-techs etc. | Typically none from RP | What ever is needed for areas where there are specific questions
What are their milestones for ALARA plans being prepared by? | Milestones for the outage dose estimate/goal are due for SAC review by T-2 per NPG-SPP-05.2.3. Therefore BFN APRs are due for completion before T-2. | We start preparing as soon as we can - a lot of plans are similar to the previous years except the dose estimates. | From our outage procedure there are 3 milestones: "Determine initial outage forecast" - this one is usually based on major scope and is given in a goal of person-Rem at T-6; "Determine Rev. 0 Dose Estimate" - this one is the driven down estimate which includes our WM software being up to date with the estimates due at T-2; "ALARA Plans Approved" - this is the ALARA plans being written and distributued to the WGs, and those requiring SAC having been taken through SAC. | See attachment | 3 months prior to outage
What does your outage org chart look like - meaning, How are your outage supervisors assigned, do you have a superintendent on each shift over the supervisors? | We have 4 superintendents. 3 are split between days and nights. 1 is acting RPM for night shift. 7 RPSS are split between days and nights and assigned to area of expertise. |  | We have 2 superintendents in the department and they split shifts, the RPM stays on days and the night shift superintendent is the designated RPM at night. The number of supervisors depends on the work that outage, we have 5 in the department full time, and will borrow at elast 2 usually from our sister station (we have 2 plants in same PA), and will hire supplementals as needed. | Days and nights have an RPM and 2-5 supervisors depending on the load/resource availability. | EACH SHIFT RP in OCC, 2supv in field. 4 flagged leads
Do you put out an ‘Outage Book’ to the site? Or RP? Or both | RP only | For the Site we put out an Outage Tri-fold showing RWP's, estimates and RP related phone numbers | Not sure what you mean by an "outage book" we have 2 control points, who will each get a binder of all the ALARA plans. The supervisors and superintendents will also get copies of these binders. Each work group gets their ALARA plans distributed to them, and we make posters with the basic RWP, task numbers, and associated setpoints | Not from RP. Our scheduling group shares an visual timeline outage plan with significant milestones. | NO
Do you do any JITT for contractors to familiarize them with your site procedures, expectations, instruments, and processes (like VSDS, HIS-20/Sentinel, etc.) | Yes | Yes we do | The road-techs that come in get a quick JITT/brief on the major jobs that outage and an overview of whats mentioned. Most don’t need sentinel unless they are helping with dosimetry or ALARA and those techs will work directly with their counterparts. | Only for significant evolutions. Last one I can remember was for SG eddy current testing. We do hold a contractor meeting to go over OE and standards/expectations but it's not JITT. | Yes site procedure review
When are ALARA Plans required to be completed? | T-2 | SAC (Station ALARA Committee) approved by E-2 | refer to above about milestones. | See attachment | 3 months prior to outage
When are RWPs required to be completed? | Already completed for years in advance. Copy and paste | E-2 | typically with ALARA plans | See attachment | 3 months prior to outage
How do you handle mass RWP Briefings? | ALARA Specialists are assigned to days and nights and complete this activity several shifts before breaker open. | We go to there location and brief | different work groups and departments will schedule briefs for their shops, these briefs will cover applicable RWPs and ALARA plans. | If we can't ensure that all attendees are engaged then the briefing will be reduced in size. | Use Large conference rooms
RWP Briefing frequency? | Depends on the level of risk. | One initial RWP Briefing unless RWP is revised. In Sentinel we at Ginna use the Authoized Individuals tab of the RWP for all Outage RWPs to ensure people are using the correct RWP and not just selecting any one. This is more time consuming for ALARA but is ensuring we are capturing the dose correctly. | As required | Guided by procedure based on risk of the work being performed | Once for RWP then Brief per entry Tailored
Is RWP Briefing frequency different than outage? |  | Yes, Online they are required to read and understand RWP themselves no Authorized Individuals tab is used. | We use different RWPs during the outage so online it is once when they first utilize that RWP, same for outage. | No | No
Do you allow any RWP self-briefing? | Yes for low risk RCA walkdowns. | Yes | yes | Yes | No
How are your outage RWP’s structured? What is your site rollout plan for outage RWP’s look like? | RWPs are written well in advance and entered onto the RWP web viewer. There is a specific milestone for TVA for outage RWP completion. | RWP's are by discipline OPS, RP, IMD, MMD, Valves, R/F, S/G any other major job. Roll out about 3 weeks before Outage start. | see attached RWP/task number poster | See attachment Outage RWPs. These typically become active at midnight for the outage. | On computer. In folders. Sent to HIT team leaders
How long in advance do they transition techs to control points? | One shift prior to breaker open | Day of Outage | The schedules will be written a month to two before, but they will start working through the control points during the week prior when we split shifts | Usually 1-2 weeks | one week prior
Personnel:
What does your ramp up and ramp down curve look like for staffing? |  | Would like people a week before Outage but mostly get them day before Outage or on Outage start | We bring everyone in the week before the otuage, then they are cut depending on where the otuage is heading, we often have lay-offs as major projects finish and then around mode 4 all contractors are gone | Most contractors usually show up the day we shutdown or the day before. | one week prior, mode 4, early outs
Do you use contractors as RP supervisors or ALARA specialists used during your outages? | Shared resources only. We will temp up RP technicians to RPSS as needed. | We use other Fleet Supervisors and aboutr three ALARA Specialists | yes, we typically will have at least one ALARA specialist (non-union), one ALARA technician, and supervisors depend on what we can get from our sister plant and what work is going on | We use a couple of them for ALARA and Dosimetry almost every outage, but rarely as supervisors. | Alara Specialists
How do your utilities shared resources support your plant’s outage organization? |  | Yes | They all support, this includes all but skeleton crews from the maintenance shops at our sister plant. | The expectation is that each site must commit to sharing with a specified site well in advance. We have always been able to fill slots by asking for volunteers but have had a scenario where we weren't able to do this due to a forced outage while other sites were doing their RFOs. | 1 sometimes two techs from one of stars plants
What position within the RP organization staffs your Outage Control Center? | Usually a RP Superintendent staffs the OCC | RP Technician Manger AND/or Fleet Corp ALARA | RP and Chemistry split that position in the OCC, it is typically a chemist for one shift, and an ALARA specialist for the other, we have also utilized an RP instructor for that | I have seen RP Scientist, Supervisor, RPM, and Training Instructor all fill this role. Typically it is the Scientist. | 2 of our 4 RP supervisors
Implementation:
How are fatigue rules managed during outage? | By TVA procedure. A rotational schedule is kept on a spreadsheet so everyone serves on the rotation. |  |  | We have a program called EmpCenter that manages it | Switch to OUTAGE rules. Work 4 on 1 off
How many control points do you operate? | Turbine Building, Reactor Building, Drywell, Turbine Deck, Lab. Sometimes major projects. | 2 Control points | 2 control points, one for containment, one for aux building | Usually two. One for containment and one for all others. Technically there is a third point for fuel handling but our Reactor Services group supplies their own RP technicians for this. | Main entrance, Containment, S/G
Are the control point coordinators house or contract personnel? | House only. | Try to have house personnel | house personnel act as leads at each CP and manage both house and road techs | Both but we try to always have at least one house tech at each for plant familiarity purposes. | Mostly house unless strong Returnee
Do you have dedicated techs for certain groups? For instance, OPS, carpenters, insulators, valve maintenance, etc. | Yes. Operations and valve maintenance. | Yes | the only groups which typically have dedicated technicians are major projects like reactor vessel internals work and SGs | No | Only S/G coverage
How are RMS/ technology needs for the outages deployed and maintained throughout the outage? |  | By IT and our house RP personnel |  | We typically have one tech on days and one on nights to manage remote monitoring tech like cameras, radios, networking, etc. | Left up year round. Staffed for outages. INST maintains