## Sheet1
South Texas Project ALARA Dose Excellence Challenge Bingo Board
Date Created | Functional Area | Initiative | Unit | Year | 5 YDOSE (REM) | Priority | Funded | Status | Owner | Due Date | Cost ($K)
Catergory : Source Term
2022 | Chemistry | Use of Hydrophobic Coatings to reduce dose from High Contamination tools/components in reactor cavity and SFP | 9 | 2024 | 0.25 | 2 | No | Pre-Planning | T Garnder | 2025-01-01 | TBD
Catergory : Shielding
2020 | Health Physics | Replace Shield Bell for Filter Changes and Moves | 9 | 2025 | 4 | 2 | No | Pre-Planning | E. Hood | 2024-06-01 | TBD
2020 | Health Physics | Inner Shield Bell for DCS Mating Device | 9 | 2025 | 1.2 | 3 | No | Pre-Planning | E. Hood | 2025-01-01 | TBD
2020 | Health Physics | Utilize Clearview Shielding for Online and Outages | 9 | 20204 | 0.15 | 4 | No | Pre-Planning | E. Hood | 2024-01-01 | TBD
2020 | Health Physics | Utilize Portable Sheild Walls for Online and Outages | 9 | 20204 | 0.15 | 4 | No | Pre-Planning | E. Hood | 2024-01-02 | TBD
Catergory : Technology
2019 | Health Physics | Deploy ARM/SRDs with Telemetry to Reduce Surveys | 9 | 2025 | 0.5 | 4 | Yes | Planning | J. Morgan | 2024-12-01 | 1700
2022 | Health Physics | Implement Dose Reports that Identifies highest dose worker for each day for ALARA suggections | 9 | 2024 | 0.15 | 4 | No | Pre-Planning | J. Morgan | 2024-12-01 | TBD
2022 | Communications | Implement VCOM to intigrate all Audion Communications throughout the both Units | 9 | 2025 | 0.15 | 2 | No | Pre-Planning | M. Perez | 2024-12-20 | 150
Catergory : Process
2024 | Work Control | Reduce Number of RCB Entries during online Activies | 9 | 2025 | 0.25 | 1 | No | Planning | M. Walker | 2024-12-30
Catergory : Behaviors
2022 | Health Physics | Reinvigorate Health Physics Webpage | 9 | 2025 | 0.05 | 4 | No | Pre-Planning | J. Morgan | 1905-07-16 | TBD
2019 | Health Physics | Implement DCS Specific ALARA Incentive Program | 9 | 2025 | 0.05 | 4 | No | Pre-Planning | A. Sosa | 2024-12-01 | 10