## Work Order Hours
Task# | Task Desc. | Job Type | Staff# | Wk Hrs | WO Tsk Hrs | LOCATION DESC | AF | RATE | EST
2 | 1RBC-HX-000A: MATERIAL ALLOCATION | OA | 1 | 1 | 1 | SHOP AREA
43 | EC423186: PERFORM F/V LEAK CHECK FOR 1" PIPING | SP | 2 | 1 | 2 | RB 2G CATWALK UNDER 1A RBCU | 0.3 | 0.36 | 0.216 | mR | 1500.12
15 | EC423186: (ELEC) WK-RDNSS OF TEMP POWER WORK FOR WELDING | SP | 3 | 5 | 15 | OFFICE WORK
12 | EC423186: (MAINT) PERFORM PRE-INSTALATION QVV WALK DOWN | SP | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.36 | 2.592 | Hours | 4167
51 | EC423186: (MECHINISTS) FABRICATE HYDRO BLANK PADDLES | SP | 2 | 20 | 40 |  | 0.3 | 0.36 | 4.32
4 | EC423186: BLAST AND COAT | OA | 2 | 8 | 16 | COMPLEX BLAST AND COAT FACILITY
16 | EC423186: ENGINEERING VFY SUITABILITY PER ASME SEC XI | SP | 1 | 1 | 1 | OFFICE WORK
6 | EC423186: ERECT SCFFOLDING | OA | 5 | 20 | 100 | R, EL.817+02
24 | EC423186: HAVE QC PERFORM A CONFIGURATION CHECK | SP | 2 | 12 | 24 | RB1, ELEV. 817 | 0.3 | 0.36 | 2.592
28 | EC423186: INSPECT/MODIFY HANGER 1-14B-0-479A-H8C | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.36 | 5.184
27 | EC423186: INSPECT/MODIFY HANGER 1-14B-0-479A-H8F | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.36 | 5.184
39 | EC423186: INSPECT/MODIFY HANGER 14-0-479A-H19 | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.36 | 5.184
52 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "A" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
55 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "A" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
53 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "B" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
56 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "B" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
54 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "C" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
57 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "C" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
9 | EC423186: INSTALL INSULATION | OA | 4 | 40 | 160 | R, EL.817+02
13 | EC423186: INSTALL TEMP POWER TO SUPPORT WELDING | SP | 3 | 5 | 15 | RB1, EL.817+02
19 | EC423186: MODIFY HANGER 1-14B-0-479A-H1 | OD | 2 | 24 | 48 | 35'-7" NORTH OF C/L, 22'-7" WEST OF C/L ELEV. 816' | 0.3 | 0.36 | 5.184
30 | EC423186: MODIFY HANGER 1-14B-0-479A-H10 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 4'EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
31 | EC423186: MODIFY HANGER 1-14B-0-479A-H11 | OD | 2 | 36 | 72 | RB1, 34 NORTH OF C/L, 11' EAST OF C/L, ELEV. 813 | 0.3 | 0.36 | 7.776
32 | EC423186: MODIFY HANGER 1-14B-0-479A-H12 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 13' EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
33 | EC423186: MODIFY HANGER 1-14B-0-479A-H13 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 16' EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
34 | EC423186: MODIFY HANGER 1-14B-0-479A-H14 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 17' EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
35 | EC423186: MODIFY HANGER 1-14B-0-479A-H15 | OD | 2 | 24 | 48 | RB1, 34'SOUTH OF C/L, 19' EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
36 | EC423186: MODIFY HANGER 1-14B-0-479A-H16 | OD | 2 | 24 | 48 | RB1, 40' NORTH OF C/L, 20' EAST OF C/L, ELEV. 813' | 0.3 | 0.36 | 5.184
37 | EC423186: MODIFY HANGER 1-14B-0-479A-H17 | OD | 2 | 36 | 72 | RB1, 44'-11" NORTH OF C/L, 22'EAST OF C/L, ELEV. 813 | 0.3 | 0.36 | 7.776
38 | EC423186: MODIFY HANGER 1-14B-0-479A-H18 | OD | 2 | 36 | 72 | RB1 43 FT NORTH OF X & 34 FT EAST OF W | 0.3 | 0.36 | 7.776
20 | EC423186: MODIFY HANGER 1-14B-0-479A-H2 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 20' WEST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
21 | EC423186: MODIFY HANGER 1-14B-0-479A-H3 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 16' WEST OF C/L, ELEV. 816 | 0.3 | 0.36 | 5.184
22 | EC423186: MODIFY HANGER 1-14B-0-479A-H4 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 13FTWEST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
23 | EC423186: MODIFY HANGER 1-14B-0-479A-H5 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 11'WEST OF C/L, ELEV. 813' | 0.3 | 0.36 | 5.184
25 | EC423186: MODIFY HANGER 1-14B-0-479A-H6 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 4' WEST OF C/L, ELEV. 816 | 0.3 | 0.36 | 5.184
26 | EC423186: MODIFY HANGER 1-14B-0-479A-H7 | OD | 2 | 24 | 48 | RB1, 34' NOTH OF C/L, 2'WEST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
29 | EC423186: MODIFY HANGER 1-14B-0-479A-H9 | OD | 2 | 24 | 48 | RB1, 35'NORTH OF C/L, 2' EAST OF C/L, ELEV. 816' | 0.3 | 0.36 | 5.184
46 | EC423186: PERFORM HYDRO FOR VT-2 TESTING | SP | 4 | 12 | 48 | R, EL.817+02 | 0.3 | 0.36 | 5.184
41 | EC423186: PREFAB BOLTING HARDWARE | OA | 2 | 36 | 72 | SHOP WORK
18 | EC423186: PREFAB HANGERS | SP | 6 | 80 | 480 | SHOP WORK
3 | EC423186: PREFAB PIPING AND COMPONENTS | SP | 6 | 120 | 720 | SHOP WORK
42 | EC423186: PRESERVICE 1" GATE VALVES AFTER WELDING | SP | 2 | 12 | 24 | SHOP WORK
44 | EC423186: QC PERFORM VT-2 INSPECTION ON 8" LPSW PIPING | FT | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.36 | 2.592
10 | EC423186: REMOVE 8", CLASS F, CS RBCU "A" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 (UNIT 1 RB LPSW PIPING TO RBCUS) | 0.3 | 0.36 | 138.24
47 | EC423186: REMOVE 8", CLASS F, CS RBCU "B" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 | 0.3 | 0.36 | 138.24
48 | EC423186: REMOVE 8", CLASS F, CS RBCU "C" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 | 0.3 | 0.36 | 138.24
40 | EC423186: REMOVE HANGER 1-14-0-479A-H71 | OD | 3 | 12 | 36 | 1RB, 26 FT EAST OF W & 49 FT NORTH OF X, ELEV. 814' | 0.3 | 0.36 | 3.888
7 | EC423186: REMOVE INSULATION | OA | 4 | 15 | 60 | R, EL.817+02
8 | EC423186: REMOVE SCFFOLDING | OA | 5 | 10 | 50 | R, EL.817+02
14 | EC423186: REMOVE TEMP POWER USED FOR WELDING | SP | 3 | 6 | 18 | R, EL.817+02
1 | EC423186: REPLACE 8", CLASS F, CS RBCU "A" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 (UNIT 1 RB LPSW PIPING TO RBCUS) | 0.3 | 0.36 | 311.04
49 | EC423186: REPLACE 8", CLASS F, CS RBCU "B" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 | 0.3 | 0.36 | 311.04
50 | EC423186: REPLACE 8", CLASS F, CS RBCU "C" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 | 0.3 | 0.36 | 311.04
45 | EC423186: SET UP HYDRO FOR VT-2 TESTING | SP | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.36 | 2.592
17 | EC423186: SETUP WELDING WORK AREA | SP | 4 | 12 | 48 | R, EL.817+02 | 0.3 | 0.36 | 5.184
5 | EC423186: TOUCH UP COATINGS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
[5 empty] | 4167 |  |  |  | 1500.12
| 20637036 | EC423186: U1 REPLACE 8", CLASS F, CS RBCU PIPE INSIDE CONTAINMENT

## REV 1
Task# | Task Desc. | Job Type | Staff# | Wk Hrs | WO Tsk Hrs | LOCATION DESC | AF | RATE | EST
2 | 1RBC-HX-000A: MATERIAL ALLOCATION | OA | 1 | 1 | 1 | SHOP AREA
43 | EC423186: PERFORM F/V LEAK CHECK FOR 1" PIPING | SP | 2 | 1 | 2 | RB 2G CATWALK UNDER 1A RBCU | 0.3 | 0.06 | 0.036 | mR | 250.02
15 | EC423186: (ELEC) WK-RDNSS OF TEMP POWER WORK FOR WELDING | SP | 3 | 5 | 15 | OFFICE WORK
12 | EC423186: (MAINT) PERFORM PRE-INSTALATION QVV WALK DOWN | SP | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.06 | 0.432 | Hours | 4167
51 | EC423186: (MECHINISTS) FABRICATE HYDRO BLANK PADDLES | SP | 2 | 20 | 40 |  | 0.3 | 0.06 | 0.72
4 | EC423186: BLAST AND COAT | OA | 2 | 8 | 16 | COMPLEX BLAST AND COAT FACILITY
16 | EC423186: ENGINEERING VFY SUITABILITY PER ASME SEC XI | SP | 1 | 1 | 1 | OFFICE WORK
6 | EC423186: ERECT SCFFOLDING | OA | 5 | 20 | 100 | R, EL.817+02
24 | EC423186: HAVE QC PERFORM A CONFIGURATION CHECK | SP | 2 | 12 | 24 | RB1, ELEV. 817 | 0.3 | 0.06 | 0.432
28 | EC423186: INSPECT/MODIFY HANGER 1-14B-0-479A-H8C | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.06 | 0.864
27 | EC423186: INSPECT/MODIFY HANGER 1-14B-0-479A-H8F | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.06 | 0.864
39 | EC423186: INSPECT/MODIFY HANGER 14-0-479A-H19 | OD | 2 | 24 | 48 | RB1 | 0.3 | 0.06 | 0.864
52 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "A" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
55 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "A" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
53 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "B" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
56 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "B" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
54 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "C" INLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
57 | EC423186: INSTALL HYDRO BLANK PADDLES ON BOTH RBCU "C" OUTLETS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.06 | 0.324
9 | EC423186: INSTALL INSULATION | OA | 4 | 40 | 160 | R, EL.817+02
13 | EC423186: INSTALL TEMP POWER TO SUPPORT WELDING | SP | 3 | 5 | 15 | RB1, EL.817+02
19 | EC423186: MODIFY HANGER 1-14B-0-479A-H1 | OD | 2 | 24 | 48 | 35'-7" NORTH OF C/L, 22'-7" WEST OF C/L ELEV. 816' | 0.3 | 0.06 | 0.864
30 | EC423186: MODIFY HANGER 1-14B-0-479A-H10 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 4'EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
31 | EC423186: MODIFY HANGER 1-14B-0-479A-H11 | OD | 2 | 36 | 72 | RB1, 34 NORTH OF C/L, 11' EAST OF C/L, ELEV. 813 | 0.3 | 0.06 | 1.296
32 | EC423186: MODIFY HANGER 1-14B-0-479A-H12 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 13' EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
33 | EC423186: MODIFY HANGER 1-14B-0-479A-H13 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 16' EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
34 | EC423186: MODIFY HANGER 1-14B-0-479A-H14 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 17' EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
35 | EC423186: MODIFY HANGER 1-14B-0-479A-H15 | OD | 2 | 24 | 48 | RB1, 34'SOUTH OF C/L, 19' EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
36 | EC423186: MODIFY HANGER 1-14B-0-479A-H16 | OD | 2 | 24 | 48 | RB1, 40' NORTH OF C/L, 20' EAST OF C/L, ELEV. 813' | 0.3 | 0.06 | 0.864
37 | EC423186: MODIFY HANGER 1-14B-0-479A-H17 | OD | 2 | 36 | 72 | RB1, 44'-11" NORTH OF C/L, 22'EAST OF C/L, ELEV. 813 | 0.3 | 0.06 | 1.296
38 | EC423186: MODIFY HANGER 1-14B-0-479A-H18 | OD | 2 | 36 | 72 | RB1 43 FT NORTH OF X & 34 FT EAST OF W | 0.3 | 0.06 | 1.296
20 | EC423186: MODIFY HANGER 1-14B-0-479A-H2 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 20' WEST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
21 | EC423186: MODIFY HANGER 1-14B-0-479A-H3 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 16' WEST OF C/L, ELEV. 816 | 0.3 | 0.06 | 0.864
22 | EC423186: MODIFY HANGER 1-14B-0-479A-H4 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 13FTWEST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
23 | EC423186: MODIFY HANGER 1-14B-0-479A-H5 | OD | 2 | 24 | 48 | RB1, 34' NORTH OF C/L, 11'WEST OF C/L, ELEV. 813' | 0.3 | 0.06 | 0.864
25 | EC423186: MODIFY HANGER 1-14B-0-479A-H6 | OD | 2 | 24 | 48 | RB1, 35' NORTH OF C/L, 4' WEST OF C/L, ELEV. 816 | 0.3 | 0.06 | 0.864
26 | EC423186: MODIFY HANGER 1-14B-0-479A-H7 | OD | 2 | 24 | 48 | RB1, 34' NOTH OF C/L, 2'WEST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
29 | EC423186: MODIFY HANGER 1-14B-0-479A-H9 | OD | 2 | 24 | 48 | RB1, 35'NORTH OF C/L, 2' EAST OF C/L, ELEV. 816' | 0.3 | 0.06 | 0.864
46 | EC423186: PERFORM HYDRO FOR VT-2 TESTING | SP | 4 | 12 | 48 | R, EL.817+02 | 0.3 | 0.06 | 0.864
41 | EC423186: PREFAB BOLTING HARDWARE | OA | 2 | 36 | 72 | SHOP WORK
18 | EC423186: PREFAB HANGERS | SP | 6 | 80 | 480 | SHOP WORK
3 | EC423186: PREFAB PIPING AND COMPONENTS | SP | 6 | 120 | 720 | SHOP WORK
42 | EC423186: PRESERVICE 1" GATE VALVES AFTER WELDING | SP | 2 | 12 | 24 | SHOP WORK
44 | EC423186: QC PERFORM VT-2 INSPECTION ON 8" LPSW PIPING | FT | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.06 | 0.432
10 | EC423186: REMOVE 8", CLASS F, CS RBCU "A" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 (UNIT 1 RB LPSW PIPING TO RBCUS) | 0.3 | 0.06 | 23.04
47 | EC423186: REMOVE 8", CLASS F, CS RBCU "B" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 | 0.3 | 0.06 | 23.04
48 | EC423186: REMOVE 8", CLASS F, CS RBCU "C" PIPING CONTAINMENT | OD | 8 | 160 | 1280 | R, EL.817+02 | 0.3 | 0.06 | 23.04
40 | EC423186: REMOVE HANGER 1-14-0-479A-H71 | OD | 3 | 12 | 36 | 1RB, 26 FT EAST OF W & 49 FT NORTH OF X, ELEV. 814' | 0.3 | 0.06 | 0.648
7 | EC423186: REMOVE INSULATION | OA | 4 | 15 | 60 | R, EL.817+02
8 | EC423186: REMOVE SCFFOLDING | OA | 5 | 10 | 50 | R, EL.817+02
14 | EC423186: REMOVE TEMP POWER USED FOR WELDING | SP | 3 | 6 | 18 | R, EL.817+02
1 | EC423186: REPLACE 8", CLASS F, CS RBCU "A" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 (UNIT 1 RB LPSW PIPING TO RBCUS) | 0.3 | 0.06 | 51.84
49 | EC423186: REPLACE 8", CLASS F, CS RBCU "B" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 | 0.3 | 0.06 | 51.84
50 | EC423186: REPLACE 8", CLASS F, CS RBCU "C" PIPING CONTAINMENT | OD | 16 | 180 | 2880 | R, EL.817+02 | 0.3 | 0.06 | 51.84
45 | EC423186: SET UP HYDRO FOR VT-2 TESTING | SP | 2 | 12 | 24 | R, EL.817+02 | 0.3 | 0.06 | 0.432
17 | EC423186: SETUP WELDING WORK AREA | SP | 4 | 12 | 48 | R, EL.817+02 | 0.3 | 0.06 | 0.864
5 | EC423186: TOUCH UP COATINGS | OA | 3 | 6 | 18 | R, EL.817+02 | 0.3 | 0.36 | 1.944
[5 empty] | 4167 |  |  |  | 250.02
| 20637036 | EC423186: U1 REPLACE 8", CLASS F, CS RBCU PIPE INSIDE CONTAINMENT